## Folha1
|  |  |  | Start | Finish
|  |  |  | 2017-03-06 | 2017-09-25 | 29
|  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September
Weeks
| Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
1 | System model and architecture refinement | Weeks 1: 16; Weeks 2: 12
2 | Setup and configuration of development enviroment | Weeks 3: 30
2.1 | Setup and Configuration | Weeks 2: 18
2.2 | Testing development environment | Weeks 3: 30
3 | Development and Prototype Implementation Phase 1 | Weeks 5: 12; Weeks 7: 20
3.1 | Secure Storage Backend Component
3.2 | Secure Storage Client Component
3.3 | Secure Transport Layer
3.4 | Homomorphic Encryption Implementation
4 | Development and Prototype Implementation Phase 2
4.1 | Setup master-slave replication
4.2
5.2
5.3
5.4
5.5
5.6
5.7
6 | Dissertation Report writing |  |  |  | 2 |  | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 |  | 4 | 6 | 16 | 4 |  |  | 16 | 8 | 8
7 | Partial Report revisions (per chapter) | Weeks 7: 2; Weeks 10: 2; Weeks 14: 2; Weeks 18: 2; Weeks 22: 2; Weeks 27: 2; Weeks 28: 2
8 | Final Report revision | Weeks 27: 12; Weeks 28: 12
9 | Publication (GitHub or xxxxx) of developed prototypes and demos | Weeks 29: 10
10 | Preparation of final exam: dissertation presentation | bar: Weeks 28 to Weeks 29
10.1 | Presentations in the context of the NOVA LINCS CR4 Research Group | Weeks 20: 4; Weeks 28: 4
10.2 | Finalization of presentation for the final exam (jury) | Weeks 28: 2; Weeks 29: 10
| Total de horas | 16 | 30 | 60 | 2 | 12 | 3 | 25 | 4 | 4 | 6 | 4 | 4 | 6 | 8 | 6 | 6 | 6 | 8 | 0 | 8 | 6 | 18 | 4 | 0 | 0 | 16 | 22 | 28 | 20 | 332
[25 empty] | ECTS | 11.8571 | Goal ECTS | 30
|  | 3.2 | 6 | 12 | 0.4 | 2.4 | 0.6 | 5 | 0.8 | 0.8 | 1.2 | 0.8 | 0.8 | 1.2 | 1.6 | 1.2 | 1.2 | 1.2 | 1.6 | 0 | 1.6 | 1.2 | 3.6 | 0.8 | 0 | 0 | 3.2 | 4.4 | 5.6 | 4
Média de horas de trabalho produtivo
|  | Segunda | Terça | Quarta | Quinta | Sexta | Sábado | Domingo | Total
|  | 6 | 6 | 4 | 6 | 4 | 4 | 4 | 34
30